|  | Weekly Team Task Report | Report #3 |
| --- | --- | --- |

| # Team: Team PiWatcher |  |  |  |  |  | Date: 10/2/2020 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project Title: Automated IoT People Counting Infrastructure |  |  |  |  |  |  |  |  |
|  | Brigham Present On-time |  | Champ Present On-time |  | Joshua Present On-time |  |  | Seth Present On-time |

### Recent Meetings:

- 9/29/2020 – Team Meeting from 3:30pm – 4:00pm
- Task followup and question refinements for client meeting

- 9/29/2020 – Client Meeting from 4:00pm – 4:30pm
- Gathered more functional/non-functional requirements

- 9/29/2020 – Team Meeting from 3:30pm – 4:00pm
- Task followup, created new tasks and set deadlines

- 10/1/2020 – Team Meeting from 3:30pm – 4:30pm
- Task followup, monthly productivity check, and set deadlines

### TASKS COMPLETED since last meeting:

| Task Title: Client-Task: Wireframe Design for back end of web application | Task Initiation: 9/17/2020 | Orig. Due Date: 9/28/2020 | Status: Complete (100%) |
| --- | --- | --- | --- |
| Who (%): Champ (100%) |  |  |  |
| Description: Draft potential wireframe design of the back end of web application |  |  |  |
| Expected Outcome: Wireframe design is uploaded on google drive, ready for review. |  |  |  |

| Task Title: Client-Task: Wireframe Design for back end of Raspberry Pi | Task Initiation: 9/17/2020 | Orig. Due Date: 9/28/2020 | Status: Complete (100%) |
| --- | --- | --- | --- |
| Who (%): Josh (100%) |  |  |  |
| Description: Draft of wireframe design for the back end of raspberry pi. |  |  |  |
| Expected Outcome: Wireframe design is uploaded onto google drive ready for review |  |  |  |

| Task Title: Client-Task: Wireframe design for front end of web application | Task Initiation: 9/17/2020 | Orig. Due Date: 9/28/2020 | Status: Complete (100%) |
| --- | --- | --- | --- |
| Who (%): Brigham (50%), Seth (50%) |  |  |  |
| Description: Wireframe design for the front end of the web application |  |  |  |
| Expected Outcome: Wireframe design is uploaded onto google drive ready for review. |  |  |  |

| Task Title: Team-Website: Implement Project Intro | Task Initiation: 9/17/2020 | Orig. Due Date: 9/28/2020 | Status: Complete (100%) |
| --- | --- | --- | --- |
| Who (%): Brigham (100%) |  |  |  |
| Description: Create project intro page with project name, graphics, team information, project sponsor information, and technical advisor information. |  |  |  |
| Expected Outcome: Website is updated, pushed on GitHub, and into production. |  |  |  |

| Task Title: Team-Website: Come up with UI design | Task Initiation: 9/17/2020 | Orig. Due Date: 9/28/2020 | Status: Complete (100%) |
| --- | --- | --- | --- |
| Who (%): Brigham (50%), Seth (50%) |  |  |  |
| Description: Create wireframe diagram of the team-website |  |  |  |
| Expected Outcome: Wireframe draft is uploaded onto the Google Drive ready for review |  |  |  |

| Task Title: Tech-Feasibility: Research and determine tech scope | Task Initiation: 9/17/2020 | Orig. Due Date: 9/28/2020 | Status: Complete (100%) |
| --- | --- | --- | --- |
| Who (%): Brigham (25%), Champ (25%), Josh (25%), Seth (25%) |  |  |  |
| Description: Determine and research different technologies and tech scopes that needs to be considered (programming languages, database technologies, networking, libraries, API designs, etc.) |  |  |  |
| Expected Outcome: Each team member has a choice for each technological scope ready for discussion next team meeting. |  |  |  |

| Task Title: Team-Website: Implement Project Details (Part 1) | Task Initiation: 9/17/2020 | Orig. Due Date: 9/28/2020 | Status: Complete (100%) |
| --- | --- | --- | --- |
| Who (%): Brigham (100%) |  |  |  |
| Description: Create project team tab/page, project description, high level requirements |  |  |  |
| Expected Outcome: Website is updated, pushed on GitHub, and into production |  |  |  |

| Task Title: Team-Website: Implement Project Details (Part 2) | Task Initiation: 9/17/2020 | Orig. Due Date: 9/28/2020 | Status: Complete (100%) |
| --- | --- | --- | --- |
| Who (%): Seth (100%) |  |  |  |
| Description: Create envisioned solution, technologies, schedule, resources, budget, codebase, link to demo |  |  |  |
| Expected Outcome: Website is updated, pushed on GitHub, and into production |  |  |  |

| Task Title: Team-Website: Check Website Quality Standards | Task Initiation: 9/17/2020 | Orig. Due Date: 9/28/2020 | Status: Complete (100%) |
| --- | --- | --- | --- |
| Who (%): Josh (50%), Seth (50%) |  |  |  |
| Description: Check if we have a clean multi-page website. Color scheme, font-size, font-style is appropriate. Check for grammar, mobile compability, and information is important |  |  |  |
| Expected Outcome: Pull request with needed changes is accepted and pushed onto production. |  |  |  |

| Task Title: Tech-Feasibility: Technological Challenges | Task Initiation: 9/29/2020 | Orig. Due Date: 10/7/2020 | Status: In progress (100%) |
| --- | --- | --- | --- |
| Who (%): Josh (100%) |  |  |  |
| Description: Define challenges for front-end, back-end, database management systems, object/image detection, and any API schemas |  |  |  |
| Expected Outcome: All possible challenges are defined and information is uploaded onto google docs |  |  |  |

### This week’s Tasks: Work plan for coming week

| Task Title: Tech-Feasibility: Cover page and table of contents | Task Initiation: 9/29/2020 | Orig. Due Date: 10/7/2020 | Status: In progress (50%) |
| --- | --- | --- | --- |
| Who (%): Seth (100%) |  |  |  |
| Description: Create the cover page for the document along with the table of contents for the following document |  |  |  |
| Expected Outcome: Cover page and table of contents is uploaded onto google docs |  |  |  |

| Task Title: Tech-Feasibility: Introduction | Task Initiation: 9/29/2020 | Orig. Due Date: 10/7/2020 | Status: In progress (0%) |
| --- | --- | --- | --- |
| Who (%): Brigs (100%) |  |  |  |
| Description: Introduce the problem that this project is trying to solve, introduce proposed solution, and the purpose of this document. |  |  |  |
| Expected Outcome: All necessary introductions are completed and the is uploaded onto google docs |  |  |  |

| Task Title: Tech-Feasibility: Technology Analysis (Part 1) | Task Initiation: 9/29/2020 | Orig. Due Date: 10/7/2020 | Status: In progress (0%) |
| --- | --- | --- | --- |
| Who (%): Brigs (100%) |  |  |  |
| Description: Establish intro to issue, alternatives, chosen approaches, and proving feasibility for front-end libraries/frameworks for our proposed solution |  |  |  |
| Expected Outcome: Information is uploaded onto google docs |  |  |  |

| Task Title: Tech-Feasibility: Technology Analysis (Part 2) | Task Initiation: 9/29/2020 | Orig. Due Date: 10/7/2020 | Status: In progress (0%) |
| --- | --- | --- | --- |
| Who (%): Champ (100%) |  |  |  |
| Description: Establish intro to issue, alternatives, chosen approaches, and proving feasibility for back-end libraries/frameworks for our proposed solution |  |  |  |
| Expected Outcome: Information is uploaded onto google docs |  |  |  |

| Task Title: Tech-Feasibility: Technology Analysis (Part 3) | Task Initiation: 9/29/2020 | Orig. Due Date: 10/7/2020 | Status: In progress (0%) |
| --- | --- | --- | --- |
| Who (%): Seth (100%) |  |  |  |
| Description: Establish intro to issue, alternatives, chosen approaches, and proving feasibility for the database management system and API schemas for our proposed solution |  |  |  |
| Expected Outcome: Information is uploaded onto google docs |  |  |  |

| Task Title: Tech-Feasibility: Technology Analysis (Part 4) | Task Initiation: 9/29/2020 | Orig. Due Date: 10/7/2020 | Status: In progress (0%) |
| --- | --- | --- | --- |
| Who (%): Josh (100%) |  |  |  |
| Description: Establish intro to issue, alternatives, chosen approaches, and proving feasibility for object/image detection software for our proposed solution |  |  |  |
| Expected Outcome: Information is uploaded onto google docs |  |  |  |

| Task Title: Tech-Feasibility: Technology Integration (Diagram and micro-solutions) | Task Initiation: 9/29/2020 | Orig. Due Date: 10/7/2020 | Status: In progress (0%) |
| --- | --- | --- | --- |
| Who (%): Champ (100%) |  |  |  |
| Description: Create a diagram of the envisioned product and provide how the micro-solutions will come together in the overall system |  |  |  |
| Expected Outcome: Diagram and information is uploaded onto google docs |  |  |  |

| Task Title: Tech-Feasibility: Technology Integration (Integration challenges & integration issues) | Task Initiation: 9/29/2020 | Orig. Due Date: 10/7/2020 | Status: In progress (0%) |
| --- | --- | --- | --- |
| Who (%): Seth (100%) |  |  |  |
| Description: Intro the integration challenges and explain potential integration issues and how it will be solved |  |  |  |
| Expected Outcome: Information is uploaded onto google docs |  |  |  |

| Task Title: Tech-Feasibility: Conclusion | Task Initiation: 9/29/2020 | Orig. Due Date: 10/7/2020 | Status: In progress (0%) |
| --- | --- | --- | --- |
| Who (%): Brigs (100%) |  |  |  |
| Description: Review project/problem and solution. Along with restating the purpose of the document, summazing all findings and providing an overall picture |  |  |  |
| Expected Outcome: Information is uploaded onto google docs |  |  |  |

### Upcoming Tasks: Planning

| Task Title: Tech Feasibility: Final Draft | Who (%): Brigham (25%), Champ (25%), Josh (25%), Seth (25%) | Rough Due Date: 10/17/2020 |
| --- | --- | --- |
| Description: Tech Feasibility rough draft is completed and on the google drive ready for team review. |  |  |

| Task Title: Requirements Document Specifications: Draft | Who (%): Brigham (25%), Champ (25%), Josh (25%), Seth (25%) | Rough Due Date: 11/4/2020 |
| --- | --- | --- |
| Description: Requirements Documents Specifications rough draft is completed and on the google drive ready for team review. |  |  |

| Task Title: Design Review 1 Presentations: Rough Draft | Who (%): Brigham (25%), Champ (25%), Josh (25%), Seth (25%) | Rough Due Date: 10/30/2020 |
| --- | --- | --- |
| Description: Design Review Rough Draft Video is ready to be presented to mentor |  |  |

### Other Problems / Other Issues:

- None problems or issues so far.